# EVENT PLAN

| Event Name: | School of Arts and Sciences Annual Symposium: "The Nexus: Space, Environment, Health, and Sustainability" |
| --- | --- |
| Event Dates: | May 8th ,2024 |
| Event Lead: | Dr. Meshal Alobaid |
| Estimated Budget: | 2,500 KD |

Vision of Event: The aim of the Spring 2024 SAS Symposium Event is to provide a platform for students across various disciplines to present their knowledge / subject of interest / academic projects, with a specific focus on senior projects, ethics considerations, technical presentations, and other courses contributing to the university's diverse academic landscape. This event serves as an opportunity for all the students to showcase their area of interest, receive feedback with subject matter experts/industry experts (Advisory boards from industry), stimulating continuous improvement towards diverse field of Arts & Science academic programs.

Provisional Logo:

Event team: Dr. Meshal Alobaid, Dr. Naheda Alkazemi, Dr. Vishal Muther, Dr. Radhika Guleri, Dr. Samer, Dr. Ali Adnan,

Time:     9:00 – 15:00                Location: Various (Building B 1st floor – Auditorium – Art Lounge)

Estimated attendance: Campus students and applicants (100-200)

# Event Elements:

| Elements of the Event | Description of Element | Lead | Stakeholders | Milestones |
| --- | --- | --- | --- | --- |
| Facilities/Inventory | Poster Hangers E-Banners Decorations Electrical Extensions | Dr. Naheda Dr. Meshal | Mr. Adnan Mr. Titus | 04/17: Site Review and overview of the plan 04/19: Request poster hangers, decorations, and Electrical Extension 04/27: Remove setup |
| IT | 4 ID Scanner 4 Laptop Auditorium support | Dr. Ali Adnan Dr. Meshal |  | 04/19: Request equipment/Support 04/27: Remove setup |
| Marketing | Event flyer design Digital Signage Social Media Posts coverage Photo & Video of the event Communication email E-Banner | Dr.Meshal Dr. Radhika | Mr. Zend Mr. Syed | 04/10: Request all relevant coverage 04/24: Confirm all requests are ready. 04/25,26, &27: Digital Signage & Social Media Posts 04/26 & 27: Ensure Marketing takes pictures and video of the event |
| Maintenance | Ensure the area is properly cleaned after each day of the event. | All team members |  | 04/19: Request support cleaning after the event 04/26&27: Confirm their support. |
| Student Conduct Officer | Ensure the safety of the students | Dr. Samir Dr. Meshal | Ms. Lina Ms. Hasnaa | 04/19: request their support. 04/24: Confirm their support. |
| Retail Operations | Food vendors will be stationed at the event. Food orders Create vouchers. F&B order | Dr. Radhika Dr.Meshal | Mr. Anto | 04/10: Initial meeting to receive vender's options & create vouchers. 04/12: Confirmation from the Vendor 04/17: Submit finance approval for vouchers. 04/24: Collect vouchers. |
| SECURITY | Food Delivery Support managing and monitoring setup/teardown crews. | Dr. Vishal Muther Dr.Meshal | Ms. Ahna Deller | 04/19: Submit all order delivery information. 04/19: Submit speakers/applicants information for access. 04/19: Request their support. 04/24: Confirm their support |
| MISC | Copy Center- Print flyer and needed documents | Dr. Vishal Muther Dr.Meshal | Mr. Jess | 04/19: Request printing flyers and all needed documents in specific dimensions 04/24: Collect all printed documents |

Additional Considerations:	Documentation Needed:

| NO | Will the press be invited? |  | Yes | Event Plan |  | YES | Location Set-Up |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NO | Will there be VIP guests invited? |  | Yes | Budget |  | NO | Weekly Action Plan |
| NO | Will clubs be involved? |  | No | Itinerary |  | NO | Run of Show |

# Project Timeline:

04/10: Marketing - Request all relevant coverage

04/10: Retail Operations - Initial meeting to receive vender's options & create vouchers

04/12: Request support from Student Affairs- Building announcement, Email invitation, and Support

04/12: Retail Operations - Confirm Vender's

04/17: Retail Operations - Submit finance approval for vouchers

04/17: Facilities: Site Review and overview of the plan

04/19: Facilities Request poster hangers, decorations, and Electrical Extension

04/19: SECURITY - Submit all order delivery information and Information for Speakers and Applicants for access

04/19: Maintenance - Request support cleaning after the event

04/19: Student Conduct Officer - request their support

04/19: SECURITY - Request their support

04/19: MISC - Request printing flyers and all needed documents in specific dimensions

04/25: Retail Operations - Collect vouchers

04/25: Marketing - Confirm all request are ready

04/25: Student Conduct Officer - Confirm their support

04/25: SECURITY - Confirm their support

04/26: MISC - Collect all printing

04/25: Email communication – Marketing email

04/25: Overview of the plan and confirm all requests

05/05: Marketing - Digital Signage & Social Media Posts

05/05: Maintenance - Confirm their support

05/05: Marketing - Ensure Marketing taking pictures and video of the event

05/05:: Site Review

# Event Logistics Reminder:

| Logistics Checklist | Include in Kick Off Meeting? | Advanced Notice Information | AIU Campus Contact | Notes |
| --- | --- | --- | --- | --- |
| Security | Yes | Large scale events: 2 weeks before, send itinerary and request for support Internal events: 1 week before, send itinerary and request for support | Anna a.deller@aiu.edu.kw | Logistics informed |
| IT Set-Up & Event Support | Yes | Inform 2 week before event of specific needs. | Mr. Mosab |  |
| Facilities | Yes | Work with defining event layout as part of planning phase, confirm set-up at least 3 days before event. | Adnan a.aslam@aiu.edu.kw |  |
| Food&Bev |  | Send final Food & Bev needs 2-3 weeks before event. | Anto a.mathew@aiu.edu.kw | It takes 1 week to coordinate vendor logistics. |
| Health & Safety | Only for elements regarding power, fire, and electric requirements. |  | Mr. Eldose Paulose | If there are any food vendors, they must be approved by Health & Safety to serve food on campus |
| AIU Campus Community Communication | Yes |  | Zend, Sayed, Ahmed, Zina, Shince Marketing team |  |
| Student Attendance Tracking | For speakers auditorium and for Poster presentation applicants |  | Mr. Mosab |  |
|  |  | phase, confirm set-up at least 3 days before event. |  |  |